## Sheet1
CONFIDENTIAL | PUBLIC * CONFIDENTIAL | [15 empty] | TARGET
The ALL important planning & development phase 4 - 6 weeks | RFP Released | 1 - 2 weeks | Walkthrough | 1 - 2 weeks | Questions Due | 1 - 2 weeks | Answers Due | 2 weeks | RFP Public Opening | 1 - 2 weeks | LOI Issued | 1 - 2 weeks | Contract Signatures | 1 - 2 weeks | Deliver Contracts Budget Division & Issue NOA | 15 - 20 days | BOE Meeting
• Plan timetable dates • Contact Agency Contract Monitor/Facility Manager to develop Scope of Work • RFP developed and reviewed by agency DAG • Evaluation committee selected & approved by agency head • Evaluation criteria & weights established • Required insurance & limits determined by Risk Management • Develop potential vendor list; request listing from State Purchasing • Schedule Evaluation Committee Meeting Video Conference Room if LV RFP based on timetable developed • Schedule a Conference Room for Evaluation Committee Meeting for CC/Reno RFP based on timetable developed | Notify potential vendors & Advertise RFP in public locations, including newspapers & websites. May post on Purchasing's website as well. |  | Mandatory on-site walkthrough. |  | Questions & clarifications submitted by vendors. Must be in writing. Contract manager and/or evaluation panel formulate answers. |  | Answers to ALL questions and clarifications provided to vendors in an Amendment to the RFP. |  | Only the names of vendors who submitted proposal are made available to the public. | RFP evaluation period and committee meeting for consensus decision of selected vendor(s). | Letter of Intent (LOI) issued to the highest scored vendor(s). Notify unsuccessful vendor(s) of the intent to award; all information is still confidential. | Negotiation period and exceptions addressed. Develop summary and contract, incorporating negotiated items, state's solicitation, contractor's response and any other required documents. | Minimum of 3 contract originals are signed. Obtain signatures from the Vendor, agency DAG, and Agency Head. |  | Contract Summary, all contracts and incorporated documents are submitted to the Budget Division for next BOE meeting. Issue Notice of Award (NOA) and post at three State buildings and Letter of Award (LOA) to successful vendor and unsuccessful vendors; RFP information & proposals become available to the public. Information marked CONFIDENTIAL by vendors is not to be released to the public. | Includes 10-day period for appeals. Only vendors who submitted a proposal may appeal. Check Budget Division website for BOE meeting and deadline dates. | Contract is effective upon BOE approval or a specific date thereafter.
*With the exception of evaluation committee and weights of evaluation criteria. Note: Names of the evaluators do not become public information. Initials only are used on all Evaluation Committee Members evaluating documents.